## GANTT
DISCO_RAP schedule |  | 2006 |  |  |  | 2007 |  |  |  | 2008 |  |  |  | 2009 |  |  |  | 2010
|  | i | ii | iii | iv | i | ii | iii | iv | i | ii | iii | iv | i | ii | iii | iv | i | ii | iii | iv
Conductor Development
1 | Preliminary development | bar: 2006 i to 2006 iv
Wire assessment and specifications drafting | bar: 2006 iv to 2007 ii
2 | Minimal GSI Rutherford cable | bar: 2007 iii to 2008 iv
Dummy cable manufacture | bar: 2006 iv to 2007 iii
3 | Optimal Requirement | bar: 2008 ii to 2009 i
Conductor ready for the winding
4 | Upgrade of INFN experimental facilities | bar: 2006 i to 2006 iii
5 | Electrical characterization of the conductors | bar: 2006 iv to 2007 i; 2008 i to 2009 iii
Cold Mass Construction
6 | Feasibility study of curved dipole | bar: 2006 i to 2006 iv
7 | Conceptual Design | bar: 2007 i to 2007 iii
8 | Tool Procurement | bar: 2007 ii to 2008 ii
Construction of winding model | bar: 2007 ii to 2008 ii
9 | Engeneering Design | bar: 2007 ii to 2008 ii
10 | Engineering for modifying/integrating LHC tool | bar: 2007 iv to 2008 ii
11 | Study of mechanical properties of materials | bar: 2007 ii to 2008 ii
Engineering Design Completed
12 | Tool Modification and Integration | bar: 2008 iii to 2009 i
13 | Materials Procurement | bar: 2008 iii to 2009 i
14 | Components Construction (Collars, Steel Laminaton, Fillers,..) | bar: 2009 i to 2009 ii
15 | Coil winding | bar: 2009 iii
16 | Collaring, yoke and containment cylinder integration | bar: 2009 iii
Cold Mass Completed
Magnet Test
17 | Design of Cryostat and Power Supply | bar: 2006 iv to 2008 ii
18 | Manufacture of Cryostat and Power Supply | bar: 2009 i to 2009 ii
19 | Commissioning of Test Station @ LASA | bar: 2009 iii
Test Station ready for the cold mass test
19 | Integration of short model into the test station ** | bar: 2008 ii; 2009 ii
20 | Test of short model | bar: 2008 ii; 2009 ii
20 | Integration of cryostated magnet into the test station | bar: 2009 iv
21 | Test of the Cold Mass | bar: 2010 i
Cold Mass Tests Completed
22 | Design of Horizontal Cryostat | bar: 2008 i to 2008 iii
23 | Manufacture of Horizontal Cryostat | bar: 2009 i to 2009 ii
24 | Acceptance Tests | bar: 2009 ii to 2009 iii
Horizontal cryostat ready
25 | Integration of Cold Mass into the Horizontal Cryostat at LASA | bar: 2010 ii
Delivery of the Magnet to GSI
Explanation
Activity | bar: 2006 i
Milestone

## Previsione di spesa
COSTS FOR THE R&D DISCO_RAP | [8 empty] | INFN int. costs
[8 empty] | GSI contr. |  | INFN Contribution to GSI
| Costs in k€ |  | 2006 | 2007 | 2008 | 2009 | TOTAL |  |  |  | 2006 |  |  | 2007 |  |  | 2008 |  |  | 2009 |  |  | 2010
| Conductor Development | [9 empty] | MI | LNF | GE | MI | LNF | GE | MI | LNF | GE | MI | LNF | GE | MI | LNF | GE
1,2,3 | Development and manufacture of Rutherford | 600 | 250 | 350 |  |  | 600 | 112 |  | 488 | 250 | - | - | 350 | - | - | 150 | - | - | - | - | - | - | - | - | 750 | 150
4 | Upgrade of INFN experimental facilities | 145 | 145 |  |  |  | 145 |  | 145 | 0 | 40 | 20 | 85 | - | - | - | - | - | - | - | - | - | - | - | - | 145 | 0
5 | Electrical characterization of the conductors | 382 | 72 | 155 | 155 |  | 382 |  | 120 | 262 | 25 | 12 | 35 | 40 | 35 | 30 | 27 | 25 | 28 | 35 | 20 | 25 |  |  |  | 337 | -45
|  | 0 | [7 empty] | 0 | [15 empty] | 0
| Prototype Design and Construction | 0 | [7 empty] | 0 | [15 empty] | 0
6,7 | Studies, Design and Follow up | 283 | 43 | 80 | 80 | 80 | 283 |  |  | 283 | 25 | 3 | 15 | 30 | 5 | 34 | 25 | 7 | 20 | 30 | 10 | 20 | 30 | 10 | 30 | 294 | 11
8 | Tool Procurement and Construction of curved winding model (Including Engineering for winding Design and Required tool) | 888 |  | 888 |  |  | 888 | 888 |  | 0 | - | - | - |  |  | 888 | [9 empty] | 888 | 0
9 | Engeneering Design | 96 |  |  | 96 |  | 96 |  |  | 96 | - | - | - | - | - | - | - | - | 96 | - | - | - | - | - | - | 96 | 0
10 | Engineering for modifying/integrating LHC tool | 36 |  |  | 36 |  | 36 |  |  | 36 | - | - | - | - | - | - | - | - | 36 | - | - | - | - | - | - | 36 | 0
11 | Study of mechanical properties of materials | 140 | 80 | 60 |  |  | 140 |  |  | 140 | 80 | - | - | 60 | - | - | - | - | - | - | - | - | - | - | - | 140 | 0
12 | Tool Modification and Integration | 264 |  |  | 264 |  | 264 |  |  | 264 | - | - | - | - | - | - | - | - | 264 | - | - | - | - | - | - | 264 | 0
13,14,15,16 | Materials and costs for cold mass construction | 625.2 |  |  | 625.2 |  | 625.2 |  |  | 625.2 | - | - | - | - | - | - | - | - | 625.2 | - | - | 235 | - | - | - | 860.2 | 235
| Magnetic Measurements | [20 empty] | 50
|  | 0 | [7 empty] | 0 | [15 empty] | 0
| Cold Mass test | 0 | [7 empty] | 0 | [15 empty] | 0
17,18,19 | Vertical Cryostat and Power Supply | 620 |  | 500 | 120 |  | 620 |  | 620 | 0 | - | - | - | 30 | - | - |  | - | - | 410 | - | - |  | - | - | 440 | -180
20,21 | Test of Cold Mass | 70 |  |  |  | 70 | 70 |  |  | 70 | - | - | - | - | - | - | - | - | - |  | - | - | 60 | - | - | 60 | -10
22,23,24 | Design and Construction of Horizontal Cryostat | 200 |  | 50 | 150 |  | 200 |  |  | 200 | - | - | - | - |  | - | - | 50 | - | - | 160 | - | - |  | - | 210 | 10
25 | Integration of Cold Mass into the Horizontal Cryostat at LASA | 50 |  |  |  | 50 | 50 |  |  | 50 | - | - | - | - | - | - | - | - | - |  | - | - | 80 | - | - | 80 | 30
|  | 0 | [7 empty] | 0 | [15 empty] | 0
| Travels | 0 | [7 empty] | 0 | [15 empty] | 0
| National Travels | 92 | 11 | 27 | 27 | 27 | 92 |  | 92 | 0 | 5 | 1 | 5 | 8 | 3 | 7 | 8 | 3 | 7 | 10 | 5 | 7 | 10 | 5 | 7 | 91 | -1
| International Travels | 274 | 34 | 80 | 80 | 80 | 274 |  | 274 | 0 | 15 | 4 | 15 | 31 | 6 | 18 | 31 | 6 | 18 | 40 | 12 | 32 | 50 | 15 | 40 | 333 | 59
|  | 0 | [7 empty] | 0
|  | 0 | [7 empty] | 0
| SubTotal | 4765.2 | 635 | 2190 | 1633.2 | 307 |  | 1000 | 1251 | 2514.2 | 440 | 40 | 155 | 549 | 49 | 977 | 241 | 91 | 1094.2 | 525 | 207 | 369 | 230 | 30 | 77
| GRAND TOTAL |  | 4765.2 |  |  |  | 4765.2 |  | 4765.2 |  | 635 |  |  | 1575 |  |  | 1426.2 |  |  | 1101 |  |  | 337 |  |  | 5074.2
[15 empty] | 5074.2 | [10 empty] | 5024.2
In yellow: internal and investment costs of INFN
The numbers on the left refer to the activities reported in the GANTT chart
| Costs Split of Main Items | [8 empty] | Progetto Ingegneristico | Progetto Ingegneristico | Studio modifiche attrezzature | Studio modifiche attrezzature |  |  |  | Modifiche attrezzature | Modifiche attrezzature | Materiali e costruzione | Materiali e costruzione
| Winding test (Construction of 1 or 2 single pole) |  | Engineering Design |  | 80 | 96 |  |  |  | 80 | [15 empty] | I.V.A. | 1.2
|  |  | Engineering Tooling |  | 120 | 144 | [5 empty] | 120 | [13 empty] | No IVA | 1
|  |  | Mandrel |  | 110 | 132 | [10 empty] | 110
|  |  | Polimerization mold |  | 100 | 120 | [10 empty] | 100
|  |  | Modification to Winding Machine |  | 150 | 180 | [10 empty] | 150
|  |  | Elastic Modulus tool |  | 30 | 36 | [10 empty] | 30
| 1200 hours |  | Manpower for winding test |  | 70 | 84 | [12 empty] | 70
|  |  | curing press |  | 60 | 72 | 888 | [9 empty] | 60
|  |  | materials |  | 20 | 24 | [12 empty] | 20
| Construction of cold mass |  | Engineering Design |  | 80 | 96 |  |  |  |  | 80 | [12 empty] | 54
|  |  | Engineering Tooling |  | 30 | 36 | [6 empty] | 30 | [10 empty] | 8
|  |  | Modification to Collaring Press and Materials |  | 110 | 132 | [11 empty] | 110 | [5 empty] | 23
|  |  | assembly desk |  | 40 | 48 | [11 empty] | 40 | [5 empty] | 44
|  |  | Supports for CERN |  | 20 | 24 | [11 empty] | 20 | [5 empty] | 7.5
|  |  | Modification of other CERN tool |  | 30 | 36 | [11 empty] | 30 | [5 empty] | 91.5
|  |  | Modification of press for lamination packing |  | 20 | 24 | [11 empty] | 20 | [5 empty] | 14
|  |  | Material for cold mass construction |  |  | 0 | [17 empty] | 50
|  |  | Collars |  | 80 | 96 | [13 empty] | 80 |  | 85 |  | 240
|  |  | Fillers |  | 40 | 48 | [13 empty] | 40 |  |  |  | 90
|  |  | Quench Heaters |  | 7 | 8.4 | [13 empty] | 7 |  |  |  | 622
|  |  | Yoke |  | 90 | 108 | [13 empty] | 90
|  |  | Other Materials |  | 14 | 16.8 | [13 empty] | 14
|  |  | SS vessel |  | 50 | 60 | [13 empty] | 50
| 3000 hours |  | Manpower |  | 240 | 288 | 1021.2 | [12 empty] | 240
[10 empty] | 80 | 80 | 120 | 30 |  |  |  | 450 | 220 | 90 | 521
[5 empty] | 1591 | 1909.2 |  |  |  | 160 |  | 150 |  |  |  |  | 670 |  | 611 |  | Con IVA
[10 empty] | 740 | [6 empty] | 851 |  |  |  | 888 |  | 1021.2
[10 empty] | 1591 | [10 empty] | 1909.2
Con IVA
[10 empty] | 96 | 96 | 144 | 36 |  |  |  | 540 | 264 | 108 | 625.2